## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
CovidHospital
[5 empty] | Legend: | Other |  |  |  |  | Unity |  |  |  |  | GUI/2D |  |  |  |  | Docs |  |  |  |  | Unassigned
Maciej Marek
Project Start Date: | 2021-03-10 |  |  |  |  | marzec | [27 empty] | kwiecień
Scrolling Increment: | 0 | time axis 2021-03-10 to 2021-05-04
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-03-10 to 2021-05-04
Analysis | Milestone |  |  | 2021-03-24 | 1 | bar: 2021-03-24
Investigating usage of covid data | Other | Adrian Końca | 50% | 2021-03-10 | 14
Brainstorming | Other | All | 70% | 2021-03-10 | 8
Technology selection | Other | All | 100% | 2021-03-10 | 7
Specification | Milestone |  |  | 2021-03-30 | 1 | bar: 2021-03-30
Goals of specifications | Docs | Krystian Lebkuchen | 40% | 2021-03-17 | 14
Gantt's chart | Docs | All | 70% | 2021-03-17 | 1
Requirements | Docs | All | 10% | 2021-03-10 | 14
UML diagrams | Docs | Krystian Lebkuchen | 0% | 2021-03-17 | 14
Verifying ideas | Other | All | 10% | 2021-03-10 | 21
Proof of Concept | Milestone |  |  | 2021-04-07 | 1 | bar: 2021-04-07
Basic game mechanics | Unity | All | 0% | 2021-03-24 | 14
GUI prototype | GUI/2D | Jakub Tarka | 0% | 2021-03-31 | 14
Save system | Unity | All | 0% | 2021-03-31 | 7
Realization | Milestone |  |  | 2021-04-21 | 1 | bar: 2021-04-21
Advanced game mechanics | Unity | All | 0% | 2021-04-07 | 21
Sprites | GUI/2D | All | 0% | 2021-04-07 | 14
Changes after POC review | Other | All | 0% | 2021-04-07 | 7
Realization | Milestone |  |  | 2021-05-26 | 1
Branches consolidation | Unity | Adrian Końca | 0% | 2021-04-28 | 14
Testing | Other | All | 0% | 2021-05-05 | 14
Finalizing documentation | Docs | Krystian Lebkuchen | 0% | 2021-05-05 | 21
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-03-23 |  |  |  |  | marzec | [13 empty] | kwiecień | [27 empty] | maj
Scrolling Increment: | 1 | time axis 2021-03-24 to 2021-05-18
Milestone description | Category | Assigned to | Progress | Start | Days | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w | ś | c | p | s | n | p | w
TITLE 1
Task 1 | Goal | Name | 25% | 2021-03-23 | 3 | ś: 2; c: 2
Task 2 | Milestone |  |  | 2021-03-28 | 1 | bar: n
Task 3 | Low Risk |  | 50% | 2021-03-20 | 10
Task 4 | Milestone |  |  | 2021-04-12 | 1 | bar: p
Task 5 | Med Risk |  | 10% | 2021-03-29 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-03-29 | 13
Task 2 | On Track |  | 50% | 2021-03-31 | 9
Task 3 | Low Risk |  | 33% | 2021-04-05 | 11
Task 4 | Milestone |  |  | 2021-04-07 | 1 | bar: ś
Task 5 |  |  |  | 2021-04-08 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-04-07 | 4
Task 2 | Med Risk |  |  | 2021-04-10 | 14
Task 3 | On Track |  |  | 2021-04-25 | 6
Task 4 | Goal |  |  | 2021-04-29 | 3 | c: 2; p: 2; s: 2
Task 5 | Low Risk |  |  | 2021-03-29 | 19
TITLE 4
Task 1 |  |  |  | 2021-05-02 | 15
Task 2 |  |  |  | 2021-05-16 | 5
Task 3 | Milestone |  |  | 2021-06-27 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-03-23 |  |  |  |  | marzec | [6 empty] | kwiecień | [27 empty] | maj
Scrolling Increment: | 5 | time axis 2021-03-28 to 2021-05-22
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-03-28 to 2021-05-22
TITLE 1
Task 1 | Goal | Name | 25% | 2021-03-23 | 3
Task 2 | Milestone |  |  | 2021-03-28 | 1 | bar: 2021-03-28
Task 3 | Low Risk |  | 50% | 2021-03-20 | 10
Task 4 | Milestone |  |  | 2021-04-12 | 1 | bar: 2021-04-12
Task 5 | Med Risk |  | 10% | 2021-03-29 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-03-29 | 13
Task 2 | On Track |  | 50% | 2021-03-31 | 9
Task 3 | Low Risk |  | 33% | 2021-04-05 | 11
Task 4 | Milestone |  |  | 2021-04-07 | 1 | bar: 2021-04-07
Task 5 |  |  |  | 2021-04-08 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-04-07 | 4
Task 2 | Med Risk |  |  | 2021-04-10 | 14
Task 3 | On Track |  |  | 2021-04-25 | 6
Task 4 | Goal |  |  | 2021-04-29 | 3 | 2021-04-29: 2; 2021-04-30: 2; 2021-05-01: 2
Task 5 | Low Risk |  |  | 2021-03-29 | 19
TITLE 4
Task 1 |  |  |  | 2021-05-02 | 15
Task 2 |  |  |  | 2021-05-16 | 5
Task 3 | Milestone |  |  | 2021-06-27 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one